C I T Y   O F   W A N N E R O O

MINUTES OF SPECIAL COUNCIL MEETING HELD IN COUNCIL CHAMBER,

ADMINISTRATION BUILDING, BOAS AVENUE, JOONDALUP,

ON WEDNESDAY 11 DECEMBER 1996

ATTENDANCES AND APOLOGIES

Councillors:   A V DAMMERS, JP - Mayor               Central Ward

F D FREAME, Deputy Mayor           South-West Ward

L O'GRADY                               North Ward

P O HEALY                               North Ward

B A COOPER                            Central Ward

L A EWEN-CHAPPELL                     Central Ward

S P MAGYAR                            Central Ward

A G TAYLOR                              South Ward

T W POPHAM                              South Ward

D K TIPPETT, JP                         South Ward

M E LYNN, JP                       South-West Ward

Chief Executive Officer:        L O DELAHAUNTY

Manager, Corporate Services:    R E DYMOCK

City Treasurer:                 J B TURKINGTON

City Building Surveyor:         R G FISHER

City Recreation and Cultural

Services Manager:             R BANHAM

City Librarian:                 N CLIFFORD

Publicity Officer:              O DAVIDSON

Committee Clerk:                J AUSTIN

In Attendance

John Main                James Christou and Partners

Hunter Beattie           Ralph and Beattie Bosworth

An apology for absence was tendered by Cr Wight.

There was one  member of the Public in attendance.

The Mayor declared the Meeting open at 2025 hrs.

PUBLIC QUESTION TIME

Nil

OC42-12/96     EXTERNAL HARD LANDSCAPING - [730-8-8-1]

Tenders received for external hard landscaping exceed  the  budget

provision.   Having regard for life cycle costing issues, cost and

appearance the Joondalup Civic  and  Cultural  Facilities  Project

Committee  recommend  the proposal using Urbanstone/Pavestone laid

to pattern with feature granite setts.

MINUTES OF SPECIAL COUNCIL MEETING - 11.12.96                    2

ADDITIONAL INFORMATION

SUMMARY

Tenders received for external hard landscaping exceed  the  budget

provision.   Having regard for life cycle costing issues, cost and

appearance the Committee recommend the proposal using  Urbanstone/

Pavestone laid to pattern with feature granite setts.

BACKGROUND

A  precis  of  the  background to this issue to provided in report

OC42-12/96.   At the Project Committee meeting on 6 December,  the

Architect advised that further prices have been called in addition

to the three in  the  original  tender.   This  resulted  in  five

options from which to make a selection.

The  drawn  details  of  each  option  will  be  presented  by the

Architect at the meeting.

The tender prices for all option are:

Option                         *Hugh & Co    Menchetti   L & S

Nominees    Coppens

1. Original Scheme             $375,317      $420,000    $546,205

with Granite Setts

2. Urbanstone/Pavestone        $364,029      $400,000    $531,611

with Granite Setts

3. Brick Paving                $305,829      400,000     $488,000

with Granite Setts

4. Urbanstone/Pavestone        $329,000      $357,000    $408,475

5. Brick Paving                $239,000      $363,000    $354,275

*Hugh and Co have subsequently  advised  that  tenders  submitted

excluded  the  cost of bitumen paving and sealing to brick paving

due an error.   The  sub-contractor  has  confirmed  tenders  for

Option  1  and  2  however has withdrawn tenders for Options 3, 4

and 5.

A comparison of lowest tenders (adjusted  for  Builder's  Margin)

and the revised budget follows:

Option                         Tenderer      Adjusted    Cost

Tender     Overrun

1. Original Scheme             Hugh & Co     $409,096    $184,096

with Granite Setts

2. Urbanstone/Pavestone        Hugh & Co     $396,792    $171,792

with Granite Setts

3. Brick Paving with           Menchetti     $436,000    $211,000

Granite Setts

4. Urbanstone/Pavestone)       Menchetti     $395,130    $170,130

5. Brick Paving                L&S Coppens   $392,160    $167,160

All tenders received are considered high.  There appears to be no

consistency in pricing between tenderers with  Menchetti  pricing

the Urbanstone/Pavestone Option 4 lower than that of brick Option

MINUTES OF SPECIAL COUNCIL MEETING - 11.12.96                    3

5. The withdrawal of Hugh and Co tenders for Options 3 and 5  has

had  a  serious  impact  on  the  viability  of  the brick paving

options.

The lack of competitive tenders has been reflected  in  the  cost

It should be noted that the Builder's pricing of options prior to

tender (as reported at a previous Occasional  Committee  meeting)

indicated  costs  ranging  from  $100,000  to  $150,000 less than

lowest tenders received.

The costing of various options to reduce costs has  now  resulted

in  the  need to award the external paving promptly.  The Builder

is concerned at the manufacturing time for materials due  to  the

amount of paving required.  Delays in awarding the works could be

reflected in a claim from the Builder for an  extension  of  time

together  with  associated  costs.   The  value of delay costs is

estimated to be approximately $19,000 per week.

The recommendation of the Project Committee stands  as  shown  on

the agenda.

Mr  John Main of James Christou and Partners, explained options of

hard landscaping as tendered, following which  Mr  Hunter  Beattie

of  Ralph  and  Beattie Bosworth outlined initial budget estimates

and variations of tenders. Councillors raised their concern at the

increase  in  costs  and  sought  advice  on  whether options were

available  to  reduce  costs,  ie  simplification  of  design  and

timeframe/possibility of re-tendering.

MOVED Cr O'Grady, SECONDED Cr Tippett that Council:

1       accepts   the   tender   of  $375,317  from  Hugh  and  Co

Contracting;

2       authorises the Architect, James Christou and Partners,  to

nominate  Hugh  and  Co Contracting to Doric Constructions

Pty Ltd;

2       authorises in accordance with Section 6.8(1) of the  Local

Government Act 1995 the following unbudgeted expenditure:

Joondalup Civic and Cultural Facilities Project  $184,000.

CARRIED BY AN

ABSOLUTE MAJORITY

SC86-12/96     TENDER:  LOOSE FURNITURE - [730-8-8-1]

Tenders  for the loose furniture exceed the budget allocation.  It

is proposed that the  scope  of  work  is  reduced  to  limit  the

additional funds required.

City  Building Surveyor gave background information on tenders for

loose furniture and explained adjustments made  to  the  furniture

requirements.

MOVED Cr Cooper, SECONDED Cr O'Grady that Council:

1       accepts  the  tender  of  $504,235.00 from Contract Office

Interiors;

MINUTES OF SPECIAL COUNCIL MEETING - 11.12.96                    4

2       authorises the signing of the contract documents;

3       authorises the City Building Surveyor to vary the contract

to reduce it to $394,040;

4       authorises  in accordance with Section 6.8(1) of the Local

Government Act 1995 the following unbudgeted expenditure:

Joondalup Civic and Cultural Facilities Project   $22,040

CARRIED BY AN

ABSOLUTE MAJORITY

There being no further business, the Chairman declared the Meeting

closed  at   2124  hrs, the following Councillors being present at

that time:

COUNCILLORS:   DAMMERS

O'GRADY

HEALY

COOPER

EWEN-CHAPPELL

MAGYAR

TAYLOR

POPHAM

FREAME

LYNN

TIPPETT